## Slide 1
BUTTONS BEBE · AI SUPPORT AGENT
Phase 2 & 3 Plan
Every feature we build next — and how long each one takes.
1
PHASE 1
Copilot — live today
2
PHASE 2
Trustworthy & Visible
3
PHASE 3
Autonomous & Multi-channel
Prepared for the meeting with Chaim · July 12, 2026

## Slide 2
PHASE 1 · LIVE TODAY
Where we are today
The agent already works as a copilot. For every incoming ticket it reads the message, pulls the order, return and product details, searches the knowledge base, and writes a first-draft reply — placed in Gorgias as a private note for your team to review and send.
The safety promise
The AI never sends on its own. Every customer reply is written by the AI but sent by a human. Sensitive tickets are flagged, never auto-handled.
~2,000 tickets / month
the volume this agent is built to take on
1
Reads every ticket
Understands the customer's message in context
2
Pulls order context
Order, return & product details, automatically
3
Searches the knowledge base
Policies, FAQs and 4,246 live products
4
Drafts the reply
Written as a private note for staff to approve
5
WhatsApp escalation
Urgent tickets ping the owner instantly
6
Notice Board
Owner posts override the AI's answers on the fly
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
2

## Slide 3
THE PLAN AT A GLANCE
Three phases — the AI earns more trust at each step
1
LIVE TODAY
Phase 1 — Copilot
The AI drafts every reply. A human reviews and sends. Read-only access to your systems.
Your team: Human sends every reply
2
NEXT · ~4–6 WEEKS
Phase 2 — Trustworthy & Visible
Make it rock-solid and higher quality, prove it learns, and give you a dashboard to see it working.
Your team: Human still approves — now with proof & metrics
3
LATER · ~3–4 MONTHS
Phase 3 — Autonomous & Multi-channel
The AI handles routine tickets end-to-end, across more channels, and can take real actions.
Your team: Human supervises the exceptions
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
3

## Slide 4
PHASE 2
Make it Trustworthy & Visible
Rock-solid, measurable, and higher quality — while the AI still drafts and a human still approves every reply.
ESTIMATE: ~4–6 WEEKS
One focused builder, delivered in small pieces so value ships every week.

## Slide 5
PHASE 2 · WHY IT MATTERS
What you get out of Phase 2
1
Fewer risky replies slip through
A second, rule-based safety net catches refunds, disputes and upset customers — not just the AI's judgment.
2
You can SEE it working
A simple dashboard: how many drafts were used as-is, tickets handled, hours saved, and the top topics.
3
Drafts get smarter weekly
The AI learns from your team's real edits — and we prove a lesson actually changes the next draft.
4
Faster, more accurate answers
Live order & tracking details in every draft, and a guardrail so it never invents a price or policy.
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
5

## Slide 6
PHASE 2 · FEATURE GROUP A
Make what we have rock-solid
The behind-the-scenes cleanup that turns a working prototype into a system you can trust in production.
1
Deterministic safety net
Code-level gate flags refunds, disputes, damaged/angry cases — backing up the AI's own judgment.
2–3 days
2
Cleaner drafts
Strip the AI's leftover self-talk and duplicated answers so drafts arrive tidy.
~1 day
3
Handle empty / junk messages
Recognise blank or survey messages and not invent a reply for them.
~½ day
4
Never invent facts or prices
A guardrail so the AI only quotes prices and policies that are actually in the knowledge base.
~1 day
5
Finish the Shopify connection
Wire live order & tracking data directly, using the correct secure login method.
~2 days
6
Fix returns tool + lock the toolset
Correct a returns lookup and restrict what the AI is allowed to touch.
~1 day
7
Security & config cleanup
One settings file, tightened secrets, and a hardened owner login page.
~1 day
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
6

## Slide 7
PHASE 2 · FEATURE GROUPS B & C
Proven learning + a window into performance
B
Learning loop, proven ON
Most of this is already built. Phase 2 turns it fully on and proves it actually helps:
1
Capture your team's real reply on each ticket
2
Review & approve the good ones (with privacy scrub)
3
Promote them so the AI can reuse them
4
PROVE a promoted lesson changes the next draft
EST: ~1 WEEK
C
Owner performance dashboard
A brand-new screen so you can see, at a glance, how the agent is doing:
Draft acceptance
% of drafts sent as-is vs edited
Tickets handled
Volume per day / week
Time saved
Estimated hours the AI saved your team
Top topics
What customers ask about most
Escalations
Sensitive tickets flagged for a human
EST: ~1–1.5 WEEKS
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
7

## Slide 8
PHASE 2 · FEATURE GROUPS D & E
Smarter context — and a first careful step toward autonomy
D
Live order & shipping status
Every draft can include the real, up-to-the-minute order status and tracking link — so “where is my order?” answers itself, accurately.
Builds on the finished Shopify connection from group A.
EST: ~1–2 DAYS
E
Auto-send pilot — ONE safe topic
Optional stretch: let the AI send its own reply for a single, very low-risk topic (order status) — behind confidence checks, the safety net, full logging, and a one-click kill switch.
Sensitive tickets are never in scope — the bridge to Phase 3.
EST: ~1 WEEK (stretch)
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
8

## Slide 9
PHASE 2 · TIMELINE
Phase 2 estimates
Focused build + test time for one person. Ranges leave room for testing and surprises.
Rock-solid foundation (group A)
~8–10 days
Learning loop, proven ON (B)
~1 week
Owner dashboard (C)
~1–1.5 weeks
Live order & shipping context (D)
~1–2 days
Auto-send pilot — stretch (E)
~1 week
Phase 2 total: ~4–6 weeks (core A–D ~4 weeks · pilot E adds ~1 week)
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
9

## Slide 10
PHASE 2 · YOUR INPUT UNBLOCKS ACCURACY
5 quick answers we need from you
The AI is only as accurate as the policies it's given. A few confirmed answers replace today's cautious placeholders.
1
Return window
How many days do customers have to return?
2
Return shipping
Who pays return postage — you or the customer?
3
Sale-season rules
Are sale / clearance items final, or returnable?
4
International rates
What's the real shipping cost outside the country?
5
Pickup vs return bin
Confirm the pickup spot and the 24/7 return-bin address.
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
10

## Slide 11
PHASE 3
Autonomous & Multi-channel
The AI handles routine tickets end-to-end, reaches customers on more channels, and can take real actions — while you supervise the exceptions.
ESTIMATE: ~3–4 MONTHS, IN STAGES
Delivered feature-by-feature — each one live before the next begins.

## Slide 12
PHASE 3 · WHY IT MATTERS
What changes for you in Phase 3
1
Routine tickets answer themselves
Common questions are resolved without a human touching them — your team focuses on the hard cases.
2
Customers reached anywhere
Not just email: website chat, Instagram & Facebook DMs, and text/WhatsApp.
3
The AI can DO things
With approval, it issues refunds, starts returns and applies discounts — not just talk about them.
Still safe: sensitive tickets — refunds you haven't approved, disputes, upset customers — always go to a human. Autonomy is switched on one topic at a time, with a kill switch.
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
12

## Slide 13
PHASE 3 · THE BIG THREE
The three biggest new capabilities
1
Auto-send graduation
Expand from the pilot to a growing set of safe, high-confidence topics — each with its own on/off switch, confidence threshold and monitoring.
2–3 weeks
2
Multi-channel
Handle conversations from website live chat, Instagram & Facebook DMs, and SMS / WhatsApp — not just email tickets.
2–4 weeks
3
Action-taking
With approval (then trusted over time): issue refunds, start & approve returns, apply discount codes, edit or cancel orders.
3–4 weeks
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
13

## Slide 14
PHASE 3 · ROUNDING IT OUT
Four more capabilities
1
Proactive & bulk handling
1–2 weeks
Spot a delay hitting many orders, auto-post a Notice, and reply in bulk — before customers even ask.
2
Multi-language at scale
1–2 weeks
Detect, reply and learn per language — reliable Hebrew and others, not just English.
3
Continuous-improvement engine
2–3 weeks
Test reply variations, auto-surface gaps in the knowledge base, and a weekly quality report.
4
Scale & reliability
1–2 weeks
Automatic retries, alerting if something breaks, and evaluating a faster / cheaper model.
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
14

## Slide 15
PHASE 3 · TIMELINE
Phase 3 estimates
Weeks of focused build per capability. Delivered in stages — not all at once.
Auto-send graduation
2–3 weeks
Multi-channel
2–4 weeks
Action-taking
3–4 weeks
Proactive & bulk
1–2 weeks
Multi-language at scale
1–2 weeks
Continuous improvement
2–3 weeks
Scale & reliability
1–2 weeks
Phase 3 total: ~3–4 months delivered feature-by-feature, each live before the next
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
15

## Slide 16
THE WHOLE PICTURE
Roadmap at a glance
NOW
Phase 1 — Copilot
Live: AI drafts, human sends
WEEKS 1–6
Phase 2 — Trustworthy & Visible
Hardening · proven learning · owner dashboard · live order data · auto-send pilot
MONTHS 2–5
Phase 3 — Autonomous & Multi-channel
Auto-send graduation · new channels · refunds/returns actions · proactive · languages · scale
Full program: ~4.5–6 months of focused build after today — with something new shipping almost every week.
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
16

## Slide 17
FROM TODAY'S MEETING
What we need to decide
1
Confirm Phase 2 priorities
Agree the order of work — and whether the auto-send pilot is in or out for now.
2
Answer the 5 policy questions
The return, shipping, sale and location details that make the AI accurate.
3
Steer Phase 3
Tell us where to lean first: more autonomy, more channels, or taking actions.
4
Line up access
When we reach new channels & actions, we'll need the relevant logins.
Next step: lock Phase 2 scope today and start on the rock-solid foundation this week.

## Slide 18
APPENDIX · FOR THE BUILD
Technical detail — Phase 2
How each Phase 2 item maps to the actual system (from CLAUDE.md, DEV-ISSUES.md and the sprint notes).
Safety net
Implement processor/classifier.py (IMMEDIATE/HIGH/NORMAL) — currently a stub returning NORMAL.
Cleaner drafts
Strip trailing self-commentary / de-dupe in hermes_runner.py (glm-5.2 verbosity, QA #01/#04/#10).
Empty messages
Guard blank / survey messages in the ticket workflow (QA #19).
Grounding
Reinforce “no price not in KB” in SOUL/prompt; add real international rate to KB (QA #03).
Shopify
Add client-credentials token minting to config.py; remove dead SHOPIFY_ADMIN_API_TOKEN (H2, #1).
Returns + toolset
Fix redo_mcp get_order mismatch (#2); restrict --yolo toolset on the Hermes call (#8).
Security / config
Consolidate the two .env files (#9); chmod 600 + rotate keys (#13); harden WhatsApp page (#12).
Learning loop
Run the spike + feedback/validate.py on 10+ tickets, then flip STUB→LIVE + add the timer.
Dashboard
New views over webhook.db + KB/learned/_ledger.json (no analytics code exists yet).
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
18

## Slide 19
APPENDIX · FOR THE BUILD
Technical notes & estimate assumptions
Phase 3 — architecture notes
Auto-send = confidence score + classifier gate + per-intent switch + kill switch + full logging.
New channels ride Gorgias' native chat / social / SMS integrations where possible.
Actions (refunds, returns, discounts, order edits) = new gated writes to Shopify & Redo — today the only write is a Gorgias internal note.
Multi-language builds on the existing multilingual KB embeddings; add per-language routing.
Model evaluation: test a less verbose / cheaper model than glm-5.2 to cut cost & cleanup.
What the estimates assume
One focused builder (Tony + Claude), working sequentially.
Estimates are build + test time; ranges absorb testing & surprises.
Chaim's 5 policy answers and any channel/action logins arrive promptly.
Scope stays fixed per item; features can be re-ordered to taste.
Days = focused work-days, not calendar days; ~1 week ≈ 5 build-days.
Buttons Bebe · AI Support Agent — Phase 2 & 3 Plan
19